Select any team name you prefer.
Please enter your name as it appears in Blackboard.
This is the priority ranking for this feature, relative to all other features.

Lower integers are higher in prioirty.

The customer may add or (for unimplemented features) remove features and change priority rankings at the start of each sprint.
This is the sprint during which the grader will grade your implementation of this feature.

By the END of this sprint, you must have implemented this feature.

If this field is blank, then this is a bonus feature. If implemented, it will be graded after the final sprint for extra credit.
This is the professor's estimate as to the relative difficulty of this feature in "points".

Points are unitless, and only have meaning relative to other estimates (a 2 point feature is expected to take about twice as long as a 1 point feature).

In a real project, points are assigned via a game of "estimating poker" played by the entire team.
Select the sprint number (1, 2, etc.) in which you plan to implement this feature. This is just for planning purposes, it won't affect your grade.

In Scrum, you only plan the current sprint, not future sprints, so you don't need to fill this in for any features not planned for the current sprint.

If you planned a "full credit" feature for the current sprint but don't complete it, then just update this cell for the next sprint. This will only affect your grade if this feature was *required* to be completed by a specific sprint, and is not.

If you planned a "bonus" or "extreme bonus" feature for the current sprint but don't complete it, and you don't want to use it for the next sprint, just use the Delete key to leave this cell blank. Your "full credit" grade will not be penalized for this decision.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
Leave blank initially (hint: Use the Delete key)
Select "In Work" when you begin designing and coding this feature.
Select "In Test" when this feature is fully coded and you are testing it.
Select Finished ONLY when the feature works well and is READY TO SHIP.
   "Finished in Sprint 1" means it was delivered at the end of Sprint 1.
   "Finished in Sprint 2" - "Finished in Sprint 6" are the same for those sprints.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
Please enter 2 or 3 capital letters that will represent you in the "Assigned To" column on each Sprint Backlog tab of this spreadsheet.
Please enter your UTA student ID number.
This is just an arbitrary unique (per sprint) integer assigned to a task, used by the team to refer to that task.
The list contains the Feature IDs from the same column on the Product Backlog tab.

For each (ahem) Feature ID, create one or more rows in this table representing the tasks you need to complete to implement that feature.

For example, for a "Provide Help to User" feature, you might assign a Feature ID of "HELP" on the Product Backlog. Then, in the Sprint Backlog table, you might have 3 rows of tasks with Feature ID of Help - "Write help text", "Create help class to display help", and "Update CLI to accept '?' command".

COPY the status cell from row 1 for each row that you add, so that you can select its status with a drop-down. This will ensure that the Sprint Burn Chart at the top updates itself automatically as you complete your tasks.
Exactly ONE team member may be responsible for any task, and they will receive grade credit for their work.

If you have more than one person on your team, each member MUST select their initials for each task the agree to perform. Use this to ensure that no duplicate work occurs, and that no tasks "fall through the cracks".

If you are wroking individually, you do NOT need to put your initials next to every task. We'll figure out who did the work. Somehow.
Select a Feature ID to the left. Then, in this column, list each discrete task needed to implement that feature.

Example tasks might be "create the Foo class", "add the Bar method to the (existing) Qux class", "Find icons for the task bar", "Update the manual to cover this feature", or "Fix the seg fault bug".

Expect roughly 3 to 10 tasks per typical feature. Don't OVER plan, but also don't just write "Implement the feature". Find a middle ground. :-)
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
   Select "Completed Day 1" if finished on the first day, and
   similarly for "Completed on Day 2" et. al.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
You may add any notes here that help understand the requirements and scope for this task
## Product Backlog
Product Name:	MICE Manager					Complete Fields in Green!!!
Team ID:	com.kevinxtung

	Team Member Name					Initials	Student ID
Required	Kevin Tung					KT	1001229434

Sprint #	Remaining	Completed This Sprint			Comment
0	37			Total	Total number of features (in column H)
1	34	3		1	Total features left at the end of Sprint #1
2	34	0		2	Total features left at the end of Sprint #2
3	34	0		3	...and so on
4	34	0
5	34	0
6	34	0

				Note: Priority of unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
				Additional features may be proposed by the student but must be approved by the Product Owner in writing
				Sprints
Feature ID	Priority	Required	Est	Planned	Status	As a...	I want to...	So that I can…	Notes
CF	1	1	13	1	Finished in Sprint 1	Manager	Create a new ice cream flavor	Stock and sell dairy products	picture not yet required, just test the classes here w/o GUI
CC	2	1	5	1	Finished in Sprint 1	Manager	Create a new container	Stock and sell dairy products	Picture not yet required
CT	3	1	5	1	Finished in Sprint 1	Manager	Create a new topping	Stock and sell better dairy products	Picture not yet required
GUI	4	2	8	2		Manager	Use a GUI instead of a terminal	Reduce training costs	This is the main window, with menu bar, tool bar, and optionally status bar
IGUI	5	2	13	2		Manager	Use dialogs to create items	Reduce training costs	One dialog should server for all items with minor variations
CS	6	2	8	2		Server	Create a serving of ice cream in a container with toppings	Create dairy products to sell	Pick a container, 1-N scoop flavors, and 0-N toppings via one or more dialogs, instance a serving object, and push on a vector
PS	7	3	5			Customer	Show the components of a serving (container, scoops, and toppings) for verification	Ensure my order was taken correctly	This is effectively a to_string method to a dialog with confirm or start over buttons
CTM	8	3	3			Manager	Create a new server	Staff the emporium
CB	9	3	2			Server	Create a new beloved customer	Keep track of our customers
CO	10	3	13			Server	Create an order of many servings of ice cream	Serve everyone in a customer party
CSB	11	3	1			Customer	Create a serving of ice cream in a container with toppings	Self-order and not have to deal with people	This just enables the Customer role to do what the Server can do in defining a serving…
COB	12	3	1			Customer	Create an order of many servings of ice cream	Self-order and not have to deal with people	...and order
CE	13	4	5			Manager	Create an emporium that stocks items and maintains a cash register	Manage the emporium	This includes item stocks, server and customer lists, and the cash register
MST	14	4	8			Manager	Manage the state of each order (unfilled -> filled -> paid, or unfilled -> canceled)	Ensure each order is filled and payment collected
SAVD	15	4	8			Manager	Save all data to a default file	Ensure our data isn’t lost
LOAD	16	4	5			Manager	Load data from a default file	Ensure our data isn’t lost
POS	17	5	5			Server	Show the servings in an order for the servers (what to prepare)	Know what to put into each serving in an order	This can simply be text in a MessageDialog, or something snazzier; probably similar to PS
POC	18	5	5			Customer	Show the servings in an order for the customer (what was ordered / how much it costs)	Verify that my order was taken correctly and see the price	This can simply be text in a MessageDialog, or something snazzier; probably similar to PS
PIX	19		21			Customer	Add and display pictures for each item (container, ice cream flavor, and topping)	Better understand the menu
CM	20		3			Owner	Create a new manager	Delegate management tasks to a pro
P&L	21		8			Manager	Add a Profit & Loss statement, showing all income, expenses, and total profit	Ensure that we’re making a profit and thus avoid bankruptcy
RI	22		5			Manager	Display an Inventory Report, listing every item and the quantity in stock	Ensure we don’t run out of any product and thus disappoint our customers
RTM	23		8			Manager	Display a Server Report, listing all info about each server including # of orders served	Better manage our team and reward productive team members
ETMS	24		8			Manager	Change a server salary	Offer promotions and pay bumps to motivate our team members
AI	25		8			Server	Restock items (ice cream flavor, container, and topping)	Ensure we can fill every order
RO	26		8			Manager	Create an Order Report, showing all pending orders (unfilled and filled but unpaid)	Better manage our production process
RB	27		5			Manager	Display a Customer Report, listing all info about each customer	Better attract repeat customers and handle complaints
EF	28		8			Manager	Edit an ice cream flavor	Improve our data and keep it synced to reality
EC	29		8			Manager	Edit a container	Improve our data and keep it synced to reality
ET	30		8			Manager	Edit a new topping	Improve our data and keep it synced to reality
ROA	31		3			Manager	Add Order Report option to show completed as well as pending orders	Review our order history seeking patterns to understand how to improve efficiency and profit
SALL	32		5			Owner	Save all data to a specified file	Franchise my company
LALL	33		5			Owner	Load data from a specified file	Franchise my company
CENEW	34		13			Owner	Create a new franchise	Franchise my company
XI	35		21			Manager	Retire an item (no longer enable its selection for a new order, but keep in reports)	Remove items no longer offered from the menu
XT	36		13			Manager	Suspend a server (no longer allow their selection for an order or restock, but keep in reports)	Remove team members who aren’t currently active from our drop-down lists (except reports)
XXT	37		5			Manager	Restore a server	Add a former team member tack into service
Product Backlog Burn Chart
Sprints
Features Remaining at end of Sprint

## Sprint 01 Backlog
Sprint #	1		Complete Fields in Green!!!
Start on	Mar 29		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Apr 05
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	3
Day 1 Left	3	0
Day 2 Left	3	0
Day 3 Left	3	0
Day 4 Left	3	0
Day 5 Left	3	0
Day 6 Left	3	0
Day 7 Left	0	3

Task ID	Feature ID	Assigned To	Description	Status	Notes
1	CF		Create a new ice cream flavor	Completed Day 7
2	CC		Create a new container	Completed Day 7
3	CT		Create a new topping	Completed Day 7
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
Sprint Burn Chart
Days
Tasks

## Sprint 02 Backlog
Sprint #	2		Complete Fields in Green!!!
Start on	Apr 05		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Apr 12
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	3
Day 1 Left	3	0
Day 2 Left	3	0
Day 3 Left	3	0
Day 4 Left	3	0
Day 5 Left	3	0
Day 6 Left	3	0
Day 7 Left	2	1

Task ID	Feature ID	Assigned To	Description	Status	Notes
1	GUI		Use a GUI instead of a terminal	Completed Day 7
2	IGUI		Use dialogs to create items	In Work
3	CS		Create a serving of ice cream in a container with toppings
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
Sprint Burn Chart
Days
Tasks

## Sprint 03 Backlog
Sprint #	3		Complete Fields in Green!!!
Start on	Apr 12		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Apr 19
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	1
Day 1 Left	1	0
Day 2 Left	1	0
Day 3 Left	1	0
Day 4 Left	1	0
Day 5 Left	1	0
Day 6 Left	1	0
Day 7 Left	1	0

Task ID	Feature ID	Assigned To	Description	Status	Notes
1			--> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
Sprint Burn Chart
Days
Tasks

## Sprint 04 Backlog
Sprint #	4		Complete Fields in Green!!!
Start on	Apr 19		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Apr 26
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	1
Day 1 Left	1	0
Day 2 Left	1	0
Day 3 Left	1	0
Day 4 Left	1	0
Day 5 Left	1	0
Day 6 Left	1	0
Day 7 Left	1	0

Task ID	Feature ID	Assigned To	Description	Status	Notes
1			--> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
Sprint Burn Chart
Days
Tasks

## Sprint 05 Backlog
Sprint #	5		Complete Fields in Green!!!
Start on	Apr 26		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	May 03
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	1
Day 1 Left	1	0
Day 2 Left	1	0
Day 3 Left	1	0
Day 4 Left	1	0
Day 5 Left	1	0
Day 6 Left	1	0
Day 7 Left	1	0

Task ID	Feature ID	Assigned To	Description	Status	Notes
1			--> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
Sprint Burn Chart
Days
Tasks